## Datix listing report
Strategic Risks - Board April 22
Risk ID | Risk - Risk Title | IF (the cause of the risk) | THEN (the event/incident) | Risk - Resulting in (the consequence) | Controls (Assurance) | Gaps in controls | Adequacy of controls | Actions to Mitigate Risk | Due date | Done date | Assurance | Gaps in assurance | Risk level (current) | Rating (current) | Risk - Rating Rationale | Risk level (Target) | Risk Appetite (Previously Used Risk Level) | Risk - Risk Appetite Rationale | Risk - Theme | Risk - Standing Committee | Date to be reviewed by | Principal objectives | Risk Lead
Risk Response - Treat
SR17 (1515) | IT Failure Due to Cyber Attack | If a sole actor or orchestrated cyber attack occurs | Then NHS Shetland could experience system downtime and/or loss of data and/or data disclosure | Resulting in disruption to services caused by system downtime, risk of delays in treatment, risk to public reputation and significant financial costs for a full system recovery | Multiple layers of technical controls in place including anti-malware, firewalls, intrusion detection, access logging, encryption, web filtering, advanced threat protection, software patching. | Limited active deployment, development and operational use of tools due to lack of resource Information Governance policies are out of date (but being redeveloped) Staff compliance with mandatory training is low (but improving) | Inadequate | Dedicated resource to ensure all digital security systems, controls and analysis are in place and actively used and reported Improve cyber training compliance Ensure NHS Shetland fully utilize the resources that will be available as part of the National NHS Cyber Centre of Excellence (not yet established but SG funding agreed) | 29/06/2022 29/06/2022 29/06/2022 |  | Reporting through established governance structure consisting fo IG subgroup, DISG, CGC Audit assurance to Audit Committee ICO and SG reporting obligations NSS have access to parts of our patching compliance in real-time |  | High risk | 16 | The cyber landscape means that mitigation against likelihood is essential not possible. By further developing security controls, monitoring and recovery testing we can mitigate against Consequence | Medium Risk | None (0 - Avoid) |  | Information Technology / Digital | Clinical Governance Committee, Digital Information Support Group, Digital Information Support Group | 2022-04-30 | 2- To provide quality, effective and safe services, delivered in the most appropriate setting for the patient, 4- To provide best value for resources and deliver financial balance, 5- To ensure sufficient organisational capacity and resilience | Chapman, Craig
Information Governance and Information Security policies are in place and available to staff.
New Information Governance and Digital Security Framework being developed to bring together all IG and Digital Security strategies, policies and procedures.
New suite of 10 digital security policies are complete and will go through approval process by end August 2021.
Cyber awareness training for staff, regular communications on cyber awareness
NHS Shetland regularly audited against cyber security by internal audit, external audit and Scottish Government. These audits are against the Network and Information Systems Regulations 2018.
SR04 (1307) | External Factors e.g. Brexit/Supply Chai | If external factors such as Brexit, changes to regulations or political instability | Then impacts on the Board's ability to sustain services, the Board’s level of mitigations including - Business continuity planning, disaster recovery plans may be limited due to the external nature of these threats | Resulting in directly impacted factors such as energy costs, food costs and medical supply constraints which would impact on patient care, performance of budgets | BREXIT group established | Current controls appear to have mitigated the initial phase of the end of the tranisition period. However controls must be maintained to ensure further developments do not place NHS Shetland at risk of disrupting care Increased costs due to the impact of leaving the single market are evident and these cannot be mitigated | Adequate | Update Board at March BD session Continue to review Information on risks / impact and use Brexit group to agree recommended actions Identify approach / structure to manage impact of No Deal Brexit in real time if necessary Communicate current position to Board members Discuss Self asessment / awareness with SG Establish BREXIT group Carry out gap analysis / risk assessment on Brexit | 19/03/2019 28/02/2022 31/12/2019 31/12/2018 12/10/2018 31/08/2018 31/10/2018 | 21/03/2019 30/07/2021 05/03/2019 15/11/2018 17/09/2018 15/11/2018 | SG Readiness checklist / assessment |  | High risk | 15 | Much remains unknown in relation to the emerging threat of the end of the transition period, it is prudent this continues to be considered a high risk Likelihood remains High because of risk of No Deal still a real possibility. Likelihood remains High because of risk of No Deal still real possibility Likelihood increased as "No Deal" becomes more likely Impact still difficult to quantify with level of information available / uncertainty around impact on supply lines Impact of Brexit on workforce and supply chain unkown. Timescale possible from late 2018 onwards | Medium Risk | Low (1 - Minimal) | Risk links to core service provision; Therefore tolerate minimal risk appetite / flexibility | Logistics / Estates | Clinical Governance Committee | 2022-05-31 | 2- To provide quality, effective and safe services, delivered in the most appropriate setting for the patient , 4- To provide best value for resources and deliver financial balance, 5- To ensure sufficient organisational capacity and resilience | Dickson, Michael
BREXIT action plan developed
Assessment of BREXIT Readiness drafted
Liaise with Scottish Government on required actions / national work
Maintaining links with National & local resilience teams to update plans
SR02 (500) | Finance | Failure to maintain financial control and delivery of recurrent savings | NHS Shetland is faced with a significant financial risk as NHS Scotland Health and Social Care medium term financial framework outlines the continued need for delivery of recurrent savings whilst redesigning services to shift the balance of care closer to home |  | Monthly budget statements, variance analysis and discussions with budget holders to ascertain issues and risks they are individually managing. | Project Management Office has established standard procedures and documentation proportionate to project size have been developed. At end of 2020-21 the gap in recurring savings was down to £1,133k. The financial plan for 2021-22 set a savings target of £2,418k to be achieved for the financial plan out-turn to achieve statutory break even position. | Adequate | Review further potential for schemes as part of 21/22 Budget management & 22/23 budget setting Board allocated task, October 2018 EMT review monthly financial position at the performance review board on a monthly basis. Maintain progress with E&R projects through Transformational Change Board that meets monthly Create additional admin, Information & Project management capacity Budget managers and their respective management accountants to work together to complete formal documentation outlining plans, risks and financial consequences of each proposal. Ensure sufficient financial information is available during the development and monitoring of the Joint Strategic Commissioning Plan | 31/03/2023 29/03/2019 31/03/2023 31/03/2020 31/03/2019 31/03/2023 31/03/2020 | 06/03/2019 31/12/2018 06/03/2019 14/02/2020 | EMT will monitor performance and assist in advice in respect of remedial action to correct adverse movements. - Monthly Progress reported regularly to Board - Bi Monthly External audit annually review the financial performance of the Board and overall guidance which are reported to the Board annually in June. The Board in 2020-21 will achieve financial balance per statutory obligation. The gap in recurring savings at the start of 2020-21 was £784k and new savings required to be achieve in 2020-21 was £1,228k giving an overall total of £2,012k. At the end of 2020-21 the savings gap unachieved on a recurring basis is at similar value to the back log value at the start of 2020-21. The Project Management Office has been recruited to and started in January 2021. As part of the initial discussions with relevant staff established baseline of projects. Standard procedures and documentation proportionate to project size have been developed. | Internal organisational capacity to support effective patient focused service review and redesign The Project Management Office has been recruited to and started in January 2021. Scottish Foundation Skills Programme for developing staff skills in service redesign. | High risk | 12 | Forecast out-turn for 2019-20 meets statutory compliance target to break-even. Currently in budget setting for 2020-21 that will identify possible new efficiency target on top of existing financial gap. Out-come of both the budget setting process and annual accounts for 2019-20 should be complete by 30 June 2020 so can re-evaluate at that date. Due to permanent medical staff vacancies in Hospital and Community locums are required essential to ensure safe staffing levels. The cost of the locums are in excess of funds available. At June 2018 Board reporting £1.2m over spend and a forecast of at least £3m over spent at year end. Reputational Damage; Loss of confidence in Board by SGHD; Impact on future delivery of clinical services. | Medium Risk | None (0 - Avoid) | In 2020/2021 NHS Shetland has achieved its statutory required out-turn position. The Board has to achieve financial balance at the yearend to meet its statutory financial obligation under section 85 of the National Health Services (Scotland) 1978. Failure to do so would result in The Auditor General under Section 22 of the Public Finance and Accountability (Scotland) Act 2000 producing an exemption audit. This audit allows the Auditor General to bring to the Parliament and the public’s attention matters of public interest related to the financial statements of public bodies. This is currently a mandatory report the Auditor General produces when NHS Boards fail to achieve yearend financial balance. Statutory NHS Shetland has a legal duty to breakeven and evidence delivery of best value for public funds. In 2018/19 current forecast projection is breakeven. | Finance | Clinical Governance Committee | 2022-06-30 | 1- To continue to improve and protect the health of the people of Shetland, 3- To redesign services where appropriate, in partnership, to ensure a modern sustainable local health service, 4- To provide best value for resources and deliver financial balance, 5- To ensure sufficient organisational capacity and resilience | Marsland, Mr Colin
Monthly review of savings made to date and future plans with the strategy on savings led by Efficiency and Redesign committee.
Finance Monitoring report to SGHD now every quarterly June to March.
Finance Monitoring report to every Board meeting.
Detailed audit of financial control and budgetary control systems on a regular basis and external audit review of annual financial position.
Annual budget setting process reviews the risks, pressure, developments and delivery of plans over a rolling 5 year period with primary focus on year 1 and 2.
Recovery plan was in place & delivered in 2018/19, 2019-20 202-21.. Plan for 2021-22 has been impacted by Covid-19 pandemic whilst plans for 2022-23 are still being developed.
Additional EMT sessions to address longer term financial plan issues Engagement with SG over draft AOP; Support for additional capacity.
Recruitment of substantive staff to vacancies, in addition to standard recruitment process using recruitment agenciies to head hunt staff
Financial plan covering 2021-22 to 2025-26 has been approved by the Board in June 2021
Project Management Office (PMO) to assist Heads of Service with redesign of services is now in place. Project Management Office (PMO) to assist Heads of Service with redesign of services.
Staff Development run locally Scottish Foundation Skills Programme for developing staff skills in service redesign. 14 waves completed and further waves are scheduled for 2021-22.
Quality Improvement Learning Session's are also run through staff development to share best practice and provide a network that includes all IJB's services.
SR01 (19) | National Standards | Negative publicity, loss of confidence in the organisation from breaches of key ACCESS targets | Negative publicity, loss of confidence in the organisation from breaches of key ACCESS targets and the potential of poorer patient outcomes as a result in delays in assessment of treatment |  | Performance management strategy in place. Active management of lists and clinics. Weekly waiting times meeting to review and manage performance. Reporting to each Board meeting. Close scrutiny by SGHD and monthly ISD reporting on performance to organisation. Ongoing discussions with off island providers. | Service Level Agreement (SLA) annual review with NHS Grampian is incomplete (mutual sign off, completion of the quality framework and KPIs to monitor the effectiveness of the commissioning process). There are some risks associated with the review of shared pathways and consideration of alternative models e.g. resilience, logistics, person centred care and affordability. There are some risks associated with capacity at NHS Grampian to deliver visiting services due to gaps in the workforce e.g. OOHs medical imaging, dermatology, max fax etc. This is a worsening picture with TTG breaches starting to be identified in some surgical specialities i.e. ophthalmology, ENT, Max fax | Inadequate | Build relationship with NHS Grampian (commissioning, sector and service level) to agree the level of service necessary to meet access targets and co-production to redesign pathways to ensure that they can be delivered sustainably Ensure that the SG Assurance Framework for waiting times reporting is in place (governance and oversight of waiting times performance) Review shared pathways with NHS Grampian and agree the redesign areas for service repatriation - including those appropriate for a focus on delivery via tele-health | 30/06/2019 01/06/2019 10/12/2019 | 06/08/2019 13/11/2019 | Performance scorecard shows the performance individual services (reported to Board) Speciality level performance is shared with clinical teams – to note achievements and pressures Early warning of TTG breaches identified through the waiting times group and rescue plans agreed accordingly Internal audit programme – reviewing the waiting times governance framework (e.g. production of patient letters) and service performance and delivery Audit Scotland Reports ISD Publications Update at Board Development Session on 20/11 about access performance Risk assessment completed to ensure funding is targeted to make the greatest impact on patient outcomes e.g. funding aligned to surgical procedures and services with no core provision | Commissioning team meetings (internal and external) are not consistently in place to manage the agenda locally and with NHS partner providers | High risk | 12 | Continued pressures as a result of increased need e.g guidelines and demographic pressures as well as workforce shortages in specific specialities. Delays in treatment for patients; Reputational damage; Failure to secure standard of service for residents; Inability to retrieve situation quickly. | Medium Risk | High (3 - Open) | We need to consider safe, innovative ways of developing services to ensure that we can deliver both access targets and evidence based practice. There are various ways in which we can do this if we take a longer term view on the workforce and creating sustainable service options. Hence, accepting there needs to be some tolerance of this risk in the short term. | Operational | Clinical Governance Committee | 2021-06-30 | 5- To ensure sufficient organisational capacity and resilience | Carolan, Kathleen
Annual commissioning discussions with NHSG take place and monthly meetings with NHSG, partners and SG are now in place. Frequency has been reduced during the pandemic but robust links in place through NHSG Clinical Board to discuss the level of elective care activity that can be delivered to Shetland around COVID peaks. Clinical prioritisation tools are being used to understand the clinical risks.
Discussion about changes and challenges in relation to elective service provision is taking place with the public through PPF and clinicians via AMC (focus on activity and implementing telehealth models)
Waiting times performance is monitored on an ongoing basis and where there are longer waiting times then recovery plans are put in place.
Access targets and trajectories set for the Operational Plan in April 2020-21. Access target performance and achievement of trajectories submitted to SG weekly. Remobilisation plan trajectories submitted in July 2021 with revised targets in light of the pandemic.
Modernising outpatient programme and elective care programme improvement ideas are being rolled out locally e.g. patient initiated follow up and opt in services (in line with realistic medicine principles). Staff developing skills from the Flow Coach Academy to build QI capacity.
Repatriation programme moved to phase 2 - identifying opportunities to streamline pathways and reduce unnecessary demand for services
AoP aligned to the Waiting Times Improvement Plan targets.
Activity identifying ways to shift to tele-health solutions to increase equitability of access
Enhanced elective care programme ageed with SG to work down the backlog of pts waiting for visiting services
SR06 (1444) | IG Training NHS Staff | Low Levels of Compliance with Mandatory IG Training | There is a risk of regulatory action and/or financial penalty and/or reputational damage to the Board as a consequence of the low level of compliance with the mandatory information governance training. There is a risk of a greater number of data incidents as a consequence of low levels of information governance awareness and knowledge due to low levels of compliance with the mandatory information governance training. |  | Information Governance is part of the Board mandatory training courses that staff should complete at commencement of employment and retake in-line with agreed refresher period in Board's plan. | The Board's performance on staff training on information governance is actively being managed with reports produced for Board Governance Committee and EMT. TURAS Learn also has line management reports that can be used as a routine tool to check staff progress in this mandatory course and all the other courses | Adequate |  |  |  | Information Governance team are now sending out pro-actively management information reports to the Executive Directors and designate line managers that allow them to identify staff compliance with completing necessary training. This will allow line mangers to ensure all direct reports are compliant with training in information governance and also completed 1 of the mandatory training modules. In respect of the Board's Governance structure performance on this is being reported to IGSG and eISG along with EMT. These reports indicated only 51.2% of staff completed on-line course at 3 March 2021. At 31 March 2021 highest current pass rate in any directorate was 96%. | Information Governance team was established that will support training and compliance monitoring. | High risk | 12 | Compliance with training would appear to have stalled as current rate at 1 July 2021 was still 62% so no change in compliance rate over last 2 months in staff completing training. May have reached another plateau that further concerted effort required to boost training compliance to reach threshold of 75%. Whilst the level of compliance is improving (as of 30th April it has risen to 62%) a compliance level of less than 75% would be likely to attract criticism from the ICO in the event of a significant incident or an ICO audit. The level of compliance has remained below 40% for a number of years. This has been highlighted in audit on several occasions. In addition, the ICO has commented on the importance of up-to-date IG training in a number of recently reported incidents. | Low risk | Low (1 - Minimal) | The low level of compliance has been raised by internal and external audit as a priority action. In addition, the ICO has emphasised the need to evidence the delivery of adequate and effective information governance training as requirement of data protection legislation (GDPR/DPA 2018). | Information Technology / Digital | Staff Governance Committee | 2022-04-30 | 2- To provide quality, effective and safe services, delivered in the most appropriate setting for the patient , 4- To provide best value for resources and deliver financial balance | Marsland, Mr Colin
In the annual staff review process line managers should be ensuring that staff that directly report to them are compliant with their statutory and mandatory training.
Information Governance team are producing reports for Directors and line managers that highlight staff compliance against this mandatory training course.
NHS Shetland has introduced an escalation procedure that can result in non-compliant staff being barred from accessing the network.
SR08 (1471) | Workforce | Workforce risk on service delivery | The risk to current and future service delivery because of:- - current method to source, supply and retain - redesign of current workforce model looking at alternative delivery models - cost of status quo is not sustainable - the ongoing mobilsation of services - looking at methods of attraction/sourcing (social media) |  | Having a remobilisation strategy and direction of travel that looks at indiviuals services and needs | Time of individuals to focus on service and workforce plans due to the impact of day-to-day service delivery | Adequate |  |  |  | The winter plan has been submitted Recovery plan completed with workforce elements Engagement on the clinical strategy Work progressing on NDI's and rediscover the Joy The process for the 3 year integrated plan going through APF SGC |  | High risk | 12 | For Nursing: Yeovil Nursing Review and link with NHS Grampian via New Zealand and Australia Primary Care looking at transformation. GP Joy looking at next recruitment campaign. Recovery Plan 4 currently underway. Integrated workforce plan to be in place by March 2022. Gaps have been fulfilled with locums or agency staff which is not effective or cost efficient. Need to understand the effects of Brexit and how that will impact on long term locums. | Medium Risk | High (3 - Open) | Currently implementing the winter workplan and phased recovery of service. | Workforce | Staff Governance Committee | 2022-03-31 | 3- To redesign services where appropriate, in partnership, to ensure a modern sustainable local health service, 4- To provide best value for resources and deliver financial balance, 5- To ensure sufficient organisational capacity and resilience | Hall, Lorraine
Revisiting and updating a clinical strategy for the next 5-10 years
Having a robust Board attraction strategy that includes succession planning and retention
SR07 (1449) | Mental Health | Alignment of MH Improvement Plans with Audit Findings | There is a risk of reputational damage and of service quality failure because of lack of the appropriate recovery plan execution from the findings of internal and external audit reports which could result in poor governance leading to a decrease in patient safety and an inability to meet both national and local service targets. |  | Board oversight of the lack of compliance to audit reports means there is are levels of accountability at all levels of the risk. | External commentary on the performance of services which undermines patient confidence in NHS services | Adequate |  |  |  | Inclusion of MH Pis in Performance reporting to IJB Presentation of updates to Audit Committee |  | Medium Risk | 9 | 2 x presentation of reports to Audit Committee outlining progress of audit actions. Good progress through actions. Significant progress in executing both audit recovery plans for mental health which has decreased the likelihood of risk realisation. Due to the high profile nature of Mental Health Services especially coming out of the current pandemic, there is high visibility and sensitivity surrounding the risk in its current form | Medium Risk | High (3 - Open) | There has already been some degree of the risk having been realised by reporting in local media as well as two different audits reports which have highlighted two different perspectives of the risk being carried by the CMHT at present with respect to waiting times and governance within the Service. Therefore with respect to recover I think we have to broaden the risk appetite profile to find ways to mitigate the risk which is acute at present and an open risk appetite represents the tempo at which the risk needs to be mitigated. | Operational | Clinical Governance Committee | 2022-07-31 | 1- To continue to improve and protect the health of the people of Shetland, 2- To provide quality, effective and safe services, delivered in the most appropriate setting for the patient , 3- To redesign services where appropriate, in partnership, to ensure a modern sustainable local health service, 4- To provide best value for resources and deliver financial balance, 5- To ensure sufficient organisational capacity and resilience | Chittick, Brian
Psychological Therapies Recovery plan formulated
Audit Action recovery plan for CMHT formulated
External OD work taken place in MH Service to support improvement plans
Clear oversight from NHSS Audit Committee regarding the audit findings with updates given to committee regularly
Good liaison between auditors and responsible officer/audit committee
External OD work taken place in MH Service to support improvement plans
Clear oversight from NHSS Audit Committee regarding the audit findings with updates given to committee regularly
Good liaison between auditors and responsible officer/audit committee
Establishment of Mental Health Executive meetings involving Medical Director and Director of Community Health and Social Care
SR09 (1482) | Clinical Governance and Assurance | If we continue with current clinical governance process via CGC | There is risk of patient harm because of incomplete governance and assurance processes which results in a poor learning system | resulting in repeat safety events and a lack of quality improvement and there is no culture of learning. | Completed the review of the role of JGG to provide a forum for system wide learning |  | Adequate | To review and refocus the clinical governance committees | 29/11/2021 | 25/08/2021 | Clinical Governance Committee |  | Medium Risk | 9 | Re-instated NHS Shetland's Clinical Governance Committee and in the process of re-establishing an organisation clinical governance meeting. There are gaps in closing off learning cycles and disseminating the learning so there is currently risk around the frequency possibility of the risk being realised. | Medium Risk | High (3 - Open) | We would be keen to take some risk to change the culture regarding the embedding of good end to end governance and assurance processes. | Training | Clinical Governance Committee | 2022-09-30 | 2- To provide quality, effective and safe services, delivered in the most appropriate setting for the patient | Brightwell, Kirsty
Linking of CG Team into clinical operational CG activity
Board wide support for SIF programme for QI work
Implementation of Performance Monitoring Group for IJB delegated services
Establishment of the Clinical Governance Committee
Visibility of a senior clinical post in clinical governance
SR12 (1354) | Capacity for Sustainable Change | If the Board’s limited capacity to oversee change could mean that changes occur in an uncontrolled manner. | Then uncontrolled change could increase risks to patient care as new processes, technology, workforce, or change is implemented without adequate consideration of its impact | Resulting in disruption to processes, unwarranted variation and untoward or unforeseen events leading to patient harm. | Provision of Service Improvement training avilable | The pandemic has placed a significant burden on NHS Shetland and the impact on our ability to recover successfully will be tested for some time to come | Adequate | The PMO has undertaken extensive engagement with the organisation to scope and refine the capacity for change in the organisation as part of the Board's articulation of it's commitment to sustainable change. However there remains further work to strengthen the link between change projects and change management and financial sustainability and the external impact of recovery from Covid 19 has yet to be fully felt | 31/03/2023 |  | Items 1 and 2 - Learning and Development plans linked to QI activity Item 3 - via QI and PMO plan Item 4 - Medical Director Item 5 - PMO reporting and annual plan | External factors such as Covid 19 funding are TBC | Medium Risk | 9 | Project management office now in place to provide a source of support to pace of service changes in the organisation. Thirteen waves of the local service improvement course have been completed. The number of staff members who have completed the nation training courses on service improvement has increased. Central support on sharing best practise and case studies service change adds support. SIFs meets monthly SIF 6 week course fully booked up over a number of month Bressay Project out to Consultation Ambulatory Care business case approved for next level Primary Care Steering group to progress action plan for EMT - September INterim CE agreed additional £20K funding into QI Service can be cautious and risk averse in relation to change. While opportunities are available for learning / development the ethos and approach of Continuous Improvement needs to be embedded in the organisation and leadership culture across and down the organisation. Service can be cautious and risk averse in relation to change; While opportunities are available for learning / development the ethos and approach of Continuous Improvement is not embedded in the organisation and leadership culture across and down the organisation | Medium risk | Significant (4 - Seek) | With the greater degree of uncertainty facing the NHS and the historical lack of change we need to take a greater degree of risk than was previously accepted, however this risk appetite is off set by the increased resilience provided by the PMO Bold changes may be required to address limitations that may occurr that may include but not limited to: 1. Staff 2. Technology 3. Remote and Rural location 4. Government Policies and targets 5. Financial resources need to be innovative and willing to take risks in implementing change; | Planning / Contingency | Clinical Governance Committee | 2022-09-30 | 1- To continue to improve and protect the health of the people of Shetland, 2- To provide quality, effective and safe services, delivered in the most appropriate setting for the patient, 3- To redesign services where appropriate, in partnership, to ensure a modern sustainable local health service, 4- To provide best value for resources and deliver financial balance, 5- To ensure sufficient organisational capacity and resilience | Dickson, Michael
Management bundles developed and in place
Service Improvement resource available to support change programme
Executive lead for SI identified
Establishment of the Project Management Support Office to support controls and transformation of change processes
SR13 (36) | Access to Services |  | Lack of access to services for those living in more remote areas of Shetland because of service configuration leading to worse outcomes for individuals |  | Models for health and social integration focus on ensuring locality resilience and sustainability. Primary healthcare continues to be provided in existing localities. | Level of influence on infrastructure planning. Understanding unmet need- where someone does not access a service | Adequate | Gather intelligence from services to identify access issues Understand reasons behind DNAS from specific service areas Focus a piece of work on sustainability in North Isles Impact assess for access for any proposed change/redesign early on in the process | 30/09/2018 28/09/2018 28/06/2019 31/03/2019 | 14/01/2019 05/11/2018 14/11/2019 26/03/2019 | DNA rates are monitored, and work in the past has not identified specific access issues for a locality - Monthly Complaints monitoring also captures access issues - Monthly DNA rates for some services are part of the Board performance report Escalation of issues from Citizens Advice Bureau and Advocacy Shetland Use of Patient Opinion | There may be individuals who have difficulties accessing services who have not sought help or flagged this to services | Medium Risk | 9 | Lack of detailed information on personal experience of access to services from all areas Lack of detailed information on personal experience of access to services from all areas | Low risk | Moderate (2 - Cautious) | Reluctant to disrupt traditional access points. New GP contract has different expectations. | Planning / Contingency | Clinical Governance Committee | 2022-06-30 | 2- To provide quality, effective and safe services, delivered in the most appropriate setting for the patient | Chittick, Brian
Outreach for care at home provided through existing care centres.
Ambulance Liaison Group well established to ensure risks identified and acted on for all ambulance issues across Shetland. Joint work in progress with Scottish Ambulance Service using the Strategic Options Framework implementation plan, with priority given to actions for remote areas. For appointments in Lerwick, there is good understanding of the need to be flexible with appointment times.
Use of Attend Anywhere Video conferencing facility is providing improved access
Merging of databases in certain localities (Walls/Bixter) allowing patients access to two teams for treatment /care to improve access
Navigation Hubs to allow remote access to care
Review of Urgent Care Pathways to decrease footfall in A&E involves use of NHS Inform/Flow
Use of Ask My GP is being scaled up across the Health Centres to provide remote access
Exploration of Health Hubs in remote areas to aid access
MDT workstream to allow individuals to see right professional earlier
Exploration of automation of AskMyGP referral project with NSS
SR10 (1489) | Business Continuity Plans | If services /departments do not have business continuity plans in place | Then there is a risk that we will not meet the Board's statutory obligations and in the event of a significant disruptive event, we will fail to deliver essential care to the population of Shetland and the recovery of services after the event will be delayed or extended unnecessarily. | Resulting in potentially harm to patients, staff, public; additional costs to the Board; reputational harm. And the post incident scrutiny by Government and regulatory/investigative bodies could lead to adverse impact on reputation of individuals and of the organisation. | Appointment of dedicated Business Continuity and Resilience Officer for NHS Shetland from 1st February 2021 on a fixed term basis to June 2022 to support services to develop and maintain plans. | Substantive dedicated BC&R Officer Gaps in service business continuity plans. Limited capacity within depts to complete the updating of plans, to train staff in business continuity planning and lack of a formal training needs assessment. A number of NHS Shetland plans not exercised and out with their planned review date. Lack of surge capacity to cover all roles in a major incident. Electronic BCM system to facilitate the development, management and performance management of BIAs and BCPs in NHS Shetland. | Adequate |  |  |  | 6 monthly reporting to EMT for the delivery of workplan Production and presentation of annual report to NHS Shetland Board Exercising and review of events / incidents test responses and produce learning and action plans that are monitored via Executive Management Team. Continual updating of Procedures and Business Continuity Plans leads to learning embedded into practice. Self assessment against Standards for organisational Resilience and appropriate plan is in place Scrutiny through Internal Audit programme | Documentation of NHS Shetland critical services. Variation in Business continuity plans. Limited assurance that exercising being planned and undertaken across the health and social care system. Limited capacity in some depts to progress BAI and BCP | Medium Risk | 8 | Response to COVID 19 has activated many business continuity plans which require updating in light of lessons learned. Response to COVID 19 has reduced capacity to keep plans up to date. EU Exit risks are actively monitored drawing capacity from the wider agenda. | Medium Risk | Moderate (2 - Cautious) | Emergency planning / business continuity based on clear processes to minimise risk & reputational damage | Planning / Contingency | Clinical Governance Committee | 2022-08-11 | 1- To continue to improve and protect the health of the people of Shetland, 2- To provide quality, effective and safe services, delivered in the most appropriate setting for the patient, 5- To ensure sufficient organisational capacity and resilience | McConnachie, James
Governance structure established to provide assurance to EMT.
Review and development of service business continuity and recovery plans with an update and review process.
Membership of Highlands and Islands Emergency Planning Group/Forum.
Fully engaged with interagency response through Shetland Emergency Planning Forum.
Reciprocal arrangement for mutual aid across North of Scotland.
Participation in national and local training and exercising programme.
Self-assessment against national Standards for Organisational Resilience and Development of prioritised action plan to be repeated in 21/22.
Sourcing of relevant training for BCP officer
SR03 (1045) | Paediatrics | we lack a specialist workforce for very sick children or children who are deteriorating | we are reliant on generalists working with remote support | the risk of an avoidable adverse event or adverse clinical outcome and leading to difficulties in recruitment and retention of generalist staff | Decision support from Paediatric Team in Aberdeen (as required). | OOHs arrangements includes GP on call model – but the majority of children are seen in A&E by Consultants or junior doctors, we need to review the OOHs arrangements for assessing children to ensure that we have the right skill mix in A&E to provide emergency care to children (particularly those who have minor illness/injury typically managed in a primary care setting). | Adequate | Progress Children's Taskforce to agree future approach to management of children and develop action plan to deliver Review the options available for OOHs service delivery (including paediatric care) and role of GP in paediatrics Develop advanced nursing practice model to support assessment of children presenting to A&E OOHs | 31/07/2019 31/07/2022 31/08/2019 | 06/06/2019 11/09/2019 | Departmental review and support of paediatric services Maternity undertake neonatal reviews Review of local cases by visiting Consultant / Retrieval services Feedback on service Review of cases through Departmental Clinical Governance systems |  | Medium Risk | 8 | Previous rationale still applies. Recent adverse events involving generalist local services. Not fully recruited to emergency medicine currently. Paediatrician recently recruited, yet to see full impact on service. Likelihood increased as a result of current issues with Senior medical staff; Increased vacancies meaning use of Locum consultants who may be less aware of local arrangements and have lower levels of confidence in managing children We have had very few adverse events relating to the clinical decision making and management of children in Shetland over the last 10-15 years that the Consultant delivered model has been in place. There are mechanisms in place to support clinical decision making (e.g. via NHS Grampian paediatricians) for Consultants and junior doctors. A national retrieval team is in place to support the emergency transfer of critically ill children. | Medium Risk | Low (1 - Minimal) | Low risk appetite due to the nature of the patients and the risk to reputational damage. Need to ensure strict risk boundaries and safety netting required. | Operational | Clinical Governance Committee | 2022-09-30 | 2- To provide quality, effective and safe services, delivered in the most appropriate setting for the patient, 3- To redesign services where appropriate, in partnership, to ensure a modern sustainable local health service, 5- To ensure sufficient organisational capacity and resilience | Brightwell, Kirsty
National Retrieval Team model (for critically ill patients).
Paediatric care review (joint discussion of cases by local Consultants, junior doctors and Paediatricians)
Training in place for clinicians (doctors and nurses) in paediatric resuscitation.
Induction in place for Locum and new Senior medical staff
Targeted training on the management of children in place for new and locum staff
Enduring Paediatric Group established with a network with NHSG
Establishment of an i-hub to ease access to paediatric care resources for all staff
Paediatrician and emergency medical physicians recruited to support generalists
New obs and gynae workforce model provides dedicated time for training specifically for neonatal care
SR05 (1427) | Covid During Recovery Period | Risk of Covid Infection in health and care facilities | There is a risk of patients accessing care in NHS Shetland health and care facilities during the pandemic recovery period transmitting or acquiring Covid-19 which would result in potential harm to staff/patients/clients in these settings. |  | Robust protocols for patients entering elective pathways including testing and shielding | Constraints of covid testing | Adequate |  |  |  | Daily reporting to SG on carehome and hiospital status |  | Medium Risk | 6 | Despite increase in cases numbers, poor medical outcomes and harm have been mitigated significantly by vaccination programme No vaccination There is still an infrequent number of positive cases which acts to remind us that the virus may still be prevalent in communities from which patients are coming to our facilities. | Medium Risk | Low (1 - Minimal) | We do not have the resources in Shetland to avoid the risk completely by, for example, running specific red and green sites. Even within GBH we have to run a green and red pathways which de fascto means we have to accept some risk within our risk profile but we would aim to mitigate as much as possible this risk profile aligned with a minimal risk appetite. | Public Health | Clinical Governance Committee | 2022-06-30 | 1- To continue to improve and protect the health of the people of Shetland, 2- To provide quality, effective and safe services, delivered in the most appropriate setting for the patient, 3- To redesign services where appropriate, in partnership, to ensure a modern sustainable local health service | Chittick, Brian
Primary care adoption of telephone and digital triage to decrease footfall in health centres
Establishment of quality assurance group for Care Homes
Alignment with national guidance regarding the wearing of masks in health and care settings
Weekly testing of care home staff
Testing of patients over 70 admitted into GBH
Establishment of "clean green" pathway for elective patients using Ronas Ward
Frequent involvement of Consultant Microbiologist in clinical decision making
Weekly testing of staff
SR11 (1451) | IG Training Non NHS Staff | IG training for staff not employed by NHS Shetland | There is a risk of harm to patients and/or staff, reputational damage, legal action and financial penalty because NHS Shetland does not have a robust mechanism to assure itself that non-NHS Shetland staff (e.g. contractors and agency locums) with access to NHS Shetland systems have adequate information governance training. This could increase the number and severity of personal data breaches. |  | Line manager engaging external individuals should ensure locums and other temporary have adequate training in information governance before commencement and ensure that local induction for these individuals highlight roles and responsibility for information governance. If not adequately assured then should ensure during induction the Board's mandatory information governance course is under taken and appropriate policies brought to their attention. | No Gaps in Controls | Adequate |  |  |  | Policy outlines responsibility for managers | A mechanism is needed to audit and report the number of non-NHS Shetland staff who have an acceptable level of IG training | Medium Risk | 6 | If an incident occured and that an untrained external employee was responsible, this could increase the potential for increased financial penalties from the regulator | Low risk | None (0 - Avoid) | Statutory obligations in respect of information governance and confidentiality to uphold for organisation reputation. In determining organisations corporate response to meeting statutory obligation the Information Commissioner Office place a high emphasis on effective staff training and regular refreshers in their reviews. With reference to the 'Reputation' domain: Because of a) the legal obligation to protect personal data and maintain public trust in the security of the highly sensitive information managed by NHS Shetland, b) the adverse media consequences of a data breach as a result of inadequately screening/enforcement of IG training for non-NHS Shetland staff and c) the potential for enforcement action by the regulator, the Data Protection Officer considers 'Avoid' to be the most appropriate response to this risk, i.e. 'No tolerance for any decisions that could lead to scrutiny of, or indeed attention to, the organisation. External interest in the organisation viewed with concern. | Training | Staff Governance Committee | 2022-04-30 | 2- To provide quality, effective and safe services, delivered in the most appropriate setting for the patient . | Morgan, Mr David
External parties engaged through a procurement process prior to a contract being awarded should ensure the information governance standards are built in to the contract and during the procurement process evidence of bidders knowledge and compliance on GDPR is established.
Risk Response - Tolerate
SR16 (1507) | Covid Outbreak | If there is a large outbreak of covid in Shetland and / or a new variant | then it could overwhelm current services through both significant increase in morbidity and demand for services and /or impact on services due to isolation of staff | resulting in significant adverse outcomes for patients and damage to NHS Shetland's reputation | Surveillance -including recruitment of fixed term PH analyst | Outwith our control - impact of new variants and potential for vaccines to be less effective Lack of capacity in Health Protection Team - two part time nurses on fixed term contracts until June 2022, require to be substantiveposts . Lack of specialist consultant level Health Proctection expertise and leadership -currently reliant on single handed consultant who currently has role of interim DPH Virus is now widespread in Shetland with increasingly daily rates , and now impossible to contain because of current national policy and reduction in national requirements for testing isolation, contact tracing and reduced restrictions No clear national policy / plans for Test & Protect & surge capacity (in case of new variants) going forward Uncertainty over requirements for future vaccine boosters and universal offer for children | Adequate | [5 empty] | High risk | 12 | Success of vaccination programme means that that the consequences of covid infection are much reduced - people now far less likely to have severe illness, require hospitalisation or die. Main disruption to health services is due to the continuing requirements for isolation. There are a number of mitigating actions in place. Full impact of these will not be realised until vaccination programme complete (including boosters), health protection team is fully staffed and asymptomatic testing more embedded. | Medium Risk | None (0 - Avoid) |  | Public Health | Clinical Governance Committee | 2022-05-11 | 1- To continue to improve and protect the health of the people of Shetland, 2- To provide quality, effective and safe services, delivered in the most appropriate setting for the patient, 5- To ensure sufficient organisational capacity and resilience | Laidlaw, Dr Susan
Timely & accurate symptomatic testing utilising both local lab and UK Gov scheme
Surge capacity for mobile testing in outbreak or increased prevalence situations
Public communications and messaging – regular and consistent
Early identification and management of outbreaks by health protection team
Established contact tracing team in place til September 2022 , with surge capacity
Support for isolation through Community support hub (not NHS)
Vaccination programme currently in progress locally and achieving high uptake rates, with planning for next phase
Port Health plans and procedures to help prevent import of cases
Promotion of PH preventative activities - in line with current national guidance
Public health input to high risk settings – specifically care homes, including weekly meeting of care home assurance group and support for care home staff. With IPC guidance from the IPC team. PH advice also given to clinical services in conjunction with IPC advice from IPC team.
Public health advice and interpretation of guidance for partners, other organisations and members of the public
Implementation of regular asymptomatic testing in health & care, education and some workplace settings; promotion of pre-arrival testing; implementation & promotion of universal offer for regular LFD testing
Recruitment of two part time fixed term Health Protection Nurse specialists
SR15 (1044) | Urgent/Emergency/Unscheduled Care | Risk that patients will experience delays in transfer from the outer islands of Shetland | There is a risk that patients will experience delays in transfer from the outer islands of Shetland for emergency or urgent care, resulting potentially in poorer clinical outcome. There also a risk that this reduction in flexibility and capacity with respect to inter-island transfer will cause remote and rural staff to feel unsupported in their location. This is likely to have a negative impact on recruitment and retention. |  | The controls which are in place are owned by the SAS and include: • Provision of emergency and urgent retrieval by MCA • Revised protocol circulated (clarity that Jigsaw not available) • Supporting SAS air cover from Helimed helicopters • Inter-island flights (during business hours) | Gaps in NDI nursing capability whilst remodelling of island nursing capability takes place and this will affect first responder capability | Adequate | Ensure that the specialist services air desk is established within the agreed timescales Ensure that air desk personnel have access to appropriate protocols for outer island transfer arrangements and are sufficiently orientated to use them Check that all NDI Nurses have appropriate equipment, supplies etc to be able to manage a patient for a reasonable time period in the event that there is a prolonged wait for air retrieval Check that all outer isles Health Centre’s have appropriate equipment, supplies etc to be able to manage a patient for a reasonable time period in the event that there is a prolonged wait for air retrieval Check that all outer isles SAS ambulances and personnel have appropriate equipment, supplies to be able to respond to an emergency/urgent case in conjunction with GP/Community Nurses in the locality Improve the functionality of the Ambulance Liaison Group (e.g. improve quoracy from SAS stakeholders) so that operational issues in respect of air ambulance requirements can be discussed and managed effectively | 01/02/2018 30/09/2022 31/03/2018 31/03/2018 31/03/2020 30/11/2019 | 01/02/2018 31/03/2018 31/03/2018 31/03/2020 13/09/2019 | Ensure effective de brief of each Transfer to understand impact and timing of transfer – report to Ambulance liaison group and CGC. Ensure effective provision of Information from SAS Recent review of Ambulance Liaison group membership and quoracy |  | Medium Risk | 8 | The number of times that patients have required urgent retrieval is small (approximately 12-15 transfers per year). However when it is needed it has to happen so this small number is irrelevant. If a patient requires urgent transfer and the timeframe of 3 hours+ does not fit with the patients clinical condition or other factors such as the weather mean that immediate transfer is necessary, then the clinician (GP or Non Doctor Island Nurse) can ask SAS to upgrade the response to an emergency and the Maritime Coastguard Agency (MCA) will provide air retrieval instead. The majority of urgent transfers in 2014 were completed by MCA in any case because the Jigsaw helicopter was unavailable. Based on historical experience and the data available, the likelihood of the MCA or SAS air ambulance resources being unavailable or out of range at the same time in low. In noting this, we don’t have any data on the H145 (or previous helicopter airbus models) as they very rarely come to Shetland. In light of the fact that activity levels will always be low it is difficult to quantify the probability of air ambulance or MCA resources being unavailable at the same time and the risk that creates in service provision. This aircraft is now being shared with the Western isles, Orkney and the North of Scotland so what with weather distance, icing and the possibility of simultaneous missions the likelihood of the H145 being available is not well quantified. | Medium Risk | Moderate (2 - Cautious) | We need to accept a certain amount of risk due to the nature of location in an island environment. There may scope to be in some ways innovative in how we mitigate this risk but we may be curtailed by the dependenncy on external agencies who may not accept the same risk appetite | Operational | Clinical Governance Committee | 2022-07-31 | 2- To provide quality, effective and safe services, delivered in the most appropriate setting for the patient, 3- To redesign services where appropriate, in partnership, to ensure a modern sustainable local health service, 5- To ensure sufficient organisational capacity and resilience | Chittick, Brian
Adverse events and collective learning takes placve via the Ambulance Liaison Group
There is now appropriate representation at Ambulance Liaison Group meeting with a balance between SHB and SAS with regional managers from SAS now involved
Liaison with local SAS reps to develop remote access to urgent care provided by SAS via NearMe for non-doctor islands
Liaison between SAS and DCHSC and MD to review first responder models in the outer isle's
Test of change regarding use of health hubs being explored
First responder training being rolled out in collaboration with SFRS and SAS
SR14 (961) | Estate | Failure to meet environmental targets, increased impact on the environment and increased cost | NHS Shetland has extensive risks surrounding it aged estate and inherited properties. The risk of non compliance against modern standards and environmental targets is increasing |  | Board reviews NHS Scotland SAFR report on an Annual basis; NHS Shetland produces an Annual Property and Asset Management Strategy (PAMS)Action plans for Estates & Facilities agreed | Regular reporting to Board on key environmental targets could be improved | Adequate | Ensure appropriate targets and progress are reported | 29/03/2020 | 13/02/2020 | Performance Scorecard (HEAT targets) - Bi monthly Scrutiny of HEAT targets / SAFR |  | Medium Risk | 4 | Relevant activity progressing where practical; Limited resources available to further accelerate Limited opportunity to progress (or control) further improvements Low level impact around target compliance NHS Shetland’s environmental targets are clear; Approach to improvement being developed although recognised opportunity for further progress | Medium Risk | High (3 - Open) | Willing to invest for return and look at creative / flexible solutions | Logistics / Estates | Clinical Governance Committee | 2022-09-30 | 1- To continue to improve and protect the health of the people of Shetland, 4- To provide best value for resources and deliver financial balance | Dickson, Michael
Board ensuring ongoing discussion takes place with Health Facilities Scotland and support provided
Board supports visits from HFS to discuss local position
NHS Shetland is developing a net zero plan to reflect the targets set by Scottish Government (Net Zero 2040)
Board supports the development of SCART tool within available resources
Board supports input into EAMS tool within available resources